North Muskham Neighbourhood Plan Steering Group (NMNPSG) – One Pager 12th January 2026

This ‘One Pager’ is not a summary of everything that has happened to date and only reflects the movement since the previous report.

- There are now 15 members (maximum 20). Of these 5 are parish councillors (IH,GH,NH,SP,AL) and 10 members of the public..

- Ten monthly meetings have now been held. The next meeting is on the 22nd January 2026

- Budget & Funding.

  - Invoice received last year (2024/2025) from consultant for £1,550 – Approx £500 remaining.

  - An amount of £1,700 for consultancy budgeted this year (2025/2026) – not yet used

  - Further funds required from PC given withdrawal of government grant. Awaiting meeting with NSDC and Locality of either 3rd, 10th or 12th February 2026 to determine amount of funding required from PC.

- Current Priority – To publish the survey now that it has been amended in accordance with feedback from pilot.  A flyer incorporating a link will be included in the Muskham Magazine and delivered to all households in the village. Likely to be March magazine. Hard copies will also be available at MRCC and church but emphasis is online.

- The exercise to determine all major land ownership in the parish and presenting it on an online map is 80% complete.