North Muskham Neighbourhood Plan Steering Group (NMNPSG) – One Pager 11th May 2026

This ‘One Pager’ is not a summary of everything that has happened to date and only reflects the movement since the previous report.

- There are now 15 members (maximum 20). Of these 5 are parish councillors (IH,GH,NH,SP,AL) and 10 members of the public. A recent note was sent to all members asking if they all still wished to remain in the group and there was no one that wanted to leave. The recent ‘volunteer’ section of the NP survey included 7 people expressing an interest – these have all been written to. There will need to be a first come first in approach taken as the number if more than the group maximum.

- Twelve monthly meetings have now been held. The next meeting is on the 21st May 2026

- Budget & Funding.  British Sugar have agreed to provide £250 towards the plan and it looks likely funding will have to come from PC reserves.

  - Invoice received last year (2024/2025) from consultant for £1,550 – Approx £500 remaining.

  - An amount of £1,783 budgeted (2025/2026) – Some now used on printing and leaflet delivery.  27/2 26 - £519 spent

  - Further amount of £1,700 included in working budget this year (2026/2027).

  - A further additional amount of approx. £8,000 will need to come from reserves.

- The chair of the steering group has contacted Anthony Northcote for an updated quote to complete from this point.

- The survey closed on the 15th March with a total of 248 representing 23.1 % of the entire village population. This is considered very high for this sort of survey.

- Current Priority – To analyse the survey responses and produce a summary document. GH is doing this but it is a very big task and will take some time. When complete this will be reviewed by both the Steering Group and the PC – Priorities will then be agreed and t forwarded to Anthony Northcote to incorporate into a NP.

- It is intended that the survey be released publicly as soon as possible

- The additional exceptional section on the NP survey regarding volunteering needs to be responded to and/or forwarded to the correct organisations.

- A thank you to respondents was sent out at the end of April in the Muskham Magazine and other usual channels. This will need to be followed up with some sort of summary.

- The exercise to determine all major land ownership in the parish and presenting it on an online map is 80% complete.