North Muskham Neighbourhood Plan Steering Group (NMNPSG) – One Pager 8th December 2025

This ‘One Pager’ is not a summary of everything that has happened to date and only reflects the movement since the previous report.

- There are now 15 members (maximum 20). Of these 5 are parish councillors (IH,GH,NH,SP,AL) and 10 members of the public..

- Ten monthly meetings have now been held. The next meeting is on the 11th December (note – the November meeting has been cancelled). Meetings have been scheduled through 2025.

- Budget & Funding.

  - Invoice received last year from consultant for £1,550 – Approx £600 remaining.

  - An amount of £1,700 for consultancy budgeted this year – not yet used

  - Further funds required from PC. Consultant daily rate is £525 per day. Request a further £1,500 for this year and to budget further next year based on progress at that point.

  - Will continue to look for other sources of funding but not positive thus far. Could we use NCC Councillor local budget? NSDC are discussing on the 9th December but looks like they are kicking down the road.

- Current Priority – to amend the survey in light of feedback from the pilot survey completed on 30th October. It is hoped to send the survey out to the village in February to include a flyer in the Muskham Magazine

- The exercise to determine all major land ownership in the parish and presenting it on an online map is 80% complete.

- The December meeting has been cancelled whilst awaiting the completion of the revised survey. The next meeting will be 22nd January 2026.