North Muskham Neighbourhood Plan Steering Group (NMNPSG) – One Pager 21st April 2026

This ‘One Pager’ is not a summary of everything that has happened to date and only reflects the movement since the previous report.

- There are now 15 members (maximum 20). Of these 5 are parish councillors (IH,GH,NH,SP,AL) and 10 members of the public.

- Twelve monthly meetings have now been held. The next meeting is on the 21st May 2026

- Budget & Funding.  British Sugar have agreed to provide £250 towards the plan and it looks likely funding will have to come from PC reserves.

  - Invoice received last year (2024/2025) from consultant for £1,550 – Approx £500 remaining.

  - An amount of £1,783 budgeted (2025/2026) – Some now used on printing and leaflet delivery.  27/2 26 - £519 spent

  - Further amount of £1,700 included in working budget this year (2026/2027).

  - A further additional amount of approx. £8,000 will need to come from reserves.

- The survey closed on the 15th March with a total of 248 representing 23.1 % of the entire village population. This is considered very high for this sort of survey.

- Current Priority – To analyse the survey responses and produce a summary document. GH is doing this but it is a very big task and will take some time. When complete this will be reviewed by both the Steering Group and the PC – Priorities will then be agreed and t forwarded to Anthony Northcote to incorporate into a NP.

- The additional exceptional section on the NP survey regarding volunteering needs to be responded to and/or forwarded to the correct organisations.

- A thank you to respondents will be sent out with the end of April Muskham Magazine and usual channels. This will need to be followed up with some sort of summary.

- The exercise to determine all major land ownership in the parish and presenting it on an online map is 80% complete.