North Muskham Neighbourhood Plan Steering Group (NMNPSG) – One Pager 9th February 2026

This ‘One Pager’ is not a summary of everything that has happened to date and only reflects the movement since the previous report.

- There are now 15 members (maximum 20). Of these 5 are parish councillors (IH,GH,NH,SP,AL) and 10 members of the public.

- Eleven monthly meetings have now been held. The next meeting is on the 16th April 2026 when the results of the survey will be reviewed.

- Budget & Funding.

  - Invoice received last year (2024/2025) from consultant for £1,550 – Approx £500 remaining.

  - An amount of £1,700 for consultancy budgeted this year (2025/2026) – Some now used on printing and print delivery t yet used

  - Further funds required from PC given withdrawal of government grant. Awaiting meeting with NSDC and Locality which should have been on 3rd, 10th or 12th February 2026 but has been postponed due to lack of interest! When will this now take place?

  - It is likely that further funding will be required from PC reserves.

- Current Priority – To encourage as many people as possible to complete the survey by the 15th March 2026. It has been widely published via an advert in the Muskham Magazine, a flyer in the magazine , both delivered to every household in the village. In addition it has been posted on the Muskham Messenger and village websites. Weekly reminders are also sent. As well as the online survey there is an option to complete as a hardcopy – available in church and MRCC. Councillors are requested to help encourage people to complete.

- The exercise to determine all major land ownership in the parish and presenting it on an online map is 80% complete.